## Introduction
Project Name
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Group D
| Project | DoughDoughs Online Ordering System
| Product Owner | Emma Monroy- Rincon
| Scrum Master | Michael McCory
| Development Team | Antoine Gaton and Wesley McElhinny
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
1 | User Authentication | Customers should be able to securely log in and manage their orders and account preferences. | - Users can create an account with email and password. | High | 1 | Product Owner
- Users can log in using valid credentials.
- Password recovery options are available via email.
- Multi-factor authentication is implemented for added security.
- Limited failed login attempts to prevent unauthorized access.
2 | Menu Management | Customers should be able to view and select from available menu items. | - The menu displays all available items (pizzas, sides, drinks). | Medium | 1 | Product Owner
- Customers can customize pizza size based on their selection.
- Nutritional information is provided for each item.
- Items can be added to the cart directly from the menu.
3 | Order Placement | Customers can place orders without delays or complications. | - Customers can review their cart before checkout. | Medium | 2 | Product Owner
- Secure payment options (credit card, PayPal) are integrated.
- Users receive order confirmation via email.
- Pickup or delivery options are available.
4 | Order Tracking | Customers can track the status of their orders in real-time. | - Real-time updates on order status (e.g., preparing, out for delivery). | Low | 2 | Product Owner
- Notifications via email or SMS for status changes.
- History of past orders accessible in the user profile.
5 | User Profile Management | Customers can manage account information, including addresses and payment details. | - Users can view and edit personal information (name, email, phone). | Low | 2 | Product Owner
- Sensitive changes trigger a verification email.
- Users can save multiple addresses for quicker checkout.
6 | Security and Compliance | Ensure the system is secure, protecting user data and meeting regulatory requirements. | - All user data is securely stored and encrypted. | High | 1 | Product Owner
- Compliance with PCI DSS standards for payment processing.
- Regular security audits are conducted.
- Monitoring and logging of data access for suspicious activity.
7 | Website Setup & Menu | Display the restaurant’s menu with descriptions, images, and prices. | - Menu items are displayed with descriptions, prices, and images. | High | 1 | Dev Team
- Menu is accessible on mobile and desktop devices.
8 | Customizable Ordering System | Allow customers to customize their pizza and other menu items. | - Customers can select menu items, customize orders, and receive confirmation. | High | 1 | Dev Team
9 | Billing System | Calculate and display the final price, including applicable discounts. | - Total price calculated based on item selection and customization. | High | 1 | Dev Team
- Discounts and promotions are applied.
10 | Payment Processing | Enable secure payments for orders using credit cards. | - Secure payment gateway integrated (e.g., Stripe, PayPal). | High | 1 | Dev Team
- Customers can pay with valid credit card information.
11 | Order Confirmation Notifications | Send order confirmation and allow customers to track their order status. | - Order confirmation received by email. | Medium | 2 | Dev Team
- Customers can track order status in real-time.
12 | Admin Menu Management | Allow store managers to manage menu items, prices, and promotions. | - Managers can securely add, update, or remove menu items, prices, and promotions in real-time. | Medium | 2 | Dev Team
13 | User Registration | Enable users to register an account and save order history and favorites. | - Users can register, log in, and access their order history and favorites. | Low | 2 | Dev Team
14 | Admin Sales Monitoring Panel | Provide an admin panel for viewing sales reports and order history. | - Admin panel displays detailed sales reports and order history. | Low | 2 | Dev Team
15 | Technical Support & Infrastructure Setup | Set up infrastructure and support systems for development, testing, and deployment of the platform. | - Project repository and environments are configured and accessible to the team. | High | 1 & 2 | Dev Team
- Sprint planning, review meetings, and testing are conducted.
- Infrastructure supports secure and efficient development workflows.

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 1
|  | Start date |  | 2024-10-19
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2024-10-19 | 2024-10-20 | 2024-10-21 | 2024-10-22 | 2024-10-23 | 2024-10-24 | 2024-10-25 | 2024-10-26 | 2024-10-27 | 2024-10-28 | 2024-10-29 | 2024-10-30 | 2024-10-31 | 2024-11-01
T1 | 1 | Given a user wants to create an account, When they provide a valid email and password, Then the account is created. | Antoine Gaton | 4
T2 | 1 | Given a user wants to log in, When they provide valid credentials, Then they are granted access to their account. | Wesley McElhinny | 3
T3 | 1 | Given a user has logged in, When they enable multi-factor authentication, Then additional security is added to their account. | Antoine Gaton | 4
T4 | 1 | Given a user has forgotten their password, When they request a recovery email, Then a password reset email is sent. | Wesley McElhinny | 2
T5 | 2 | Given a customer views the menu, When they access the website, Then all available items are displayed. | Wesley McElhinny | 3
T6 | 2 | Given a customer selects a pizza, When they customize the size, Then their selection is reflected in the cart. | Antoine Gaton | 3
T7 | 2 | Given a customer views a menu item, When they check its details, Then nutritional information is shown. | Wesley McElhinny | 2
T8 | 6 | Given user data is stored, When data is saved, Then it is securely encrypted to ensure compliance. | Antoine Gaton | 5
T9 | 6 | Given that PCI DSS standards are in place, When payment data is processed, Then the system complies with security standards. | Emma Monroy- Rincon | 4
T10 | 7 | Given a user is viewing the menu, When they access the site from any device, Then the menu layout adjusts for desktop or mobile. | Antoine Gaton | 3
T11 | 7 | Given a user accesses the website on mobile, When they open the menu, Then the layout is responsive. | Wesley McElhinny | 4
T12 | 8 | Given a customer orders a pizza, When they select customizations, Then the system reflects their preferences in the order summary. | Antoine Gaton | 6
T13 | 9 | Given a customer places an order, When items are selected, Then the billing system calculates total prices, including discounts. | Antoine Gaton | 5
T14 | 10 | Given a customer proceeds to checkout, When they enter payment details, Then the payment gateway securely processes the transaction. | Antoine Gaton | 6
T15 | 15 | Given development is underway, When initial setup is completed, Then the project repository is accessible to all team members. | Antoine Gaton | 3
T16 | 15 | Given testing is required, When development environments are set up, Then testing infrastructure is configured. | Wesley McElhinny | 3
|  | Remaining units (actual) |  | 64 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 2.1316e-14
[10 empty] | 0 | 60 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | DoughDoughs Online Ordering System
|  | Sprint # |  | 2
|  | Start date |  | 2024-12-10
|  |  | Total Team Members | 2
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial Estimate in HRs | 2024-12-10 | 2024-12-11 | 2024-12-12 | 2024-12-13 | 2024-12-14 | 2024-12-15 | 2024-12-16 | 2024-12-17 | 2024-12-18 | 2024-12-19 | 2024-12-20 | 2024-12-21 | 2024-12-22 | 2024-12-23
T17 | 3 | Given a customer has items in their cart, When they proceed to order placement, Then the order is successfully placed without delays. | Wesley McElhinny | 5
T18 | 3 | Given a customer is reviewing their order, When they access their cart, Then the cart displays all selected items for confirmation. | Antoine Gaton | 3
T19 | 3 | Given a customer completes their order, When payment is confirmed, Then an order confirmation email is sent. | Wesley McElhinny | 2
T20 | 4 | Given a customer has placed an order, When they track their order, Then real-time status updates are shown. | Antoine Gaton | 5
T21 | 4 | Given an order status changes, When the status is updated, Then notifications are sent via email or SMS to the customer. | Wesley McElhinny | 4
T22 | 5 | Given a customer accesses their profile, When they view or edit information, Then they can update details such as name, email, and phone. | Antoine Gaton | 5
T23 | 5 | Given a customer changes sensitive information, When an update is made, Then a verification email is sent to confirm the change. | Wesley McElhinny | 3
T24 | 11 | Given an order is confirmed, When the order is placed, Then a notification is sent with real-time tracking links. | Antoine Gaton | 3
T25 | 12 | Given a store manager accesses the menu management, When they add or update items, Then changes are saved and reflected on the menu in real time. | Antoine Gaton | 4
T26 | 12 | Given a store manager edits the menu, When they remove items, Then the items are no longer displayed in the customer menu. | Wesley McElhinny | 5
T27 | 13 | Given a customer wants to register, When they provide details, Then an account is created, allowing order history and favorites to be saved. | Wesley McElhinny | 3
T28 | 14 | Given an admin accesses sales data, When they open the admin panel, Then sales reports and order history are displayed in a detailed format. | Antoine Gaton | 6
T29 | 14 | Given sales monitoring is required, When data is accessed in the admin panel, Then the panel shows accurate reports and order history. | Wesley McElhinny | 4
T30 | 15 | Given the sprint is ending, When the sprint review is held, Then testing and feedback are gathered. | Emma Monroy- Rincon | 3
T31 | 15 | Given deployment is required, When the infrastructure setup is completed, Then the system is ready for secure deployment. | Antoine Gaton | 5
|  | Remaining units (actual) |  | 32 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A
|  | Remaining units (ideal) |  |  | 29.7143 | 27.4286 | 25.1429 | 22.8571 | 20.5714 | 18.2857 | 16 | 13.7143 | 11.4286 | 9.1429 | 6.8571 | 4.5714 | 2.2857 | 1.0658e-14
[10 empty] | 0 | 60 | [5 empty] | 0 | 0
[10 empty] | 10 | 0 | [5 empty] | 10 | 0